## Fallback (hidden)
CORT Fallback Plan
| Step | Responsibility | Duration | Comments
1 | Verify that the production backup is complete. | Upgrade Team | 15
2 | Client and PM determine fallback if necessary | PM/ Client | 15
3 | Team will restore Production database from Production Backup taken prior to MP Upgrade | Upgrade Team | 720
4 | Restore PS_HOME from backup | Upgrade Team | 60
5 | Bounce the database server. | Upgrade Team | 15
6 | Clear cache on the process scheduler and application server and bring up application server and process scheduler | Upgrade Team | 15
7 | AFS team test. | AFS Team | 360
8 | Client team test. | Client | 180
|  |  | 1380 | Total Time (minutes)
|  |  | 23 | Total Time (hours)

## Image 7 8 Tools Start 1AM
No. | Step | Duration (min) | Status | Start Time (EST) | End Time (EST) | Responsible | Comments
1 | Notify End Users of system unavailability & B92 Refresh - Pagelet Notification in PSPROD - Send out the email to end users - Set up a Net Announce - Request an IT Services page “Spotlight” update - Update Sorry Page - Address "Recurrance" jobs scheduled during outage window |  | Open | 2018-04-25 12:00 |  | Cornell
2 | Remind Developers (IBM and Cornell) to save off B92 projects (B92 will be refreshed Saturday night) - Prepare migraiton forms for 4/26 changes to be migrated to B92 AFTER refresh in step 26 |  | Open | 2018-04-26 12:00 |  | Cornell IBM PM
3 | Run Compare between P92 and A92 ** will not be needed due to addition of Tools Patch with this Project | 180 | Open | 2018-04-27 01:00 | 2018-04-27 04:00 | IBM Upgrade
4 | Place scheduled jobs on HOLD (scheduled during cutover) Notify IBM when complete Ensure there are no other jobs running (i.e. scheduled by individual users) Note: Production control will complete their job stream | 60 | Open | 2018-04-27 16:00 | 2018-04-27 17:00 | Cornell
5 | When all processing is complete DISABLE the Tidal Prod to PSPROD Connection on T3: For Image 5 -scheduled for 12:55AM | 15 | Open | 2018-04-27 22:55 |  | Cornell
6 | Cornell to notify IBM when job stream completes and IBM can proceed with Backup: For Image 5 PCU will email at appx 10:00pm (or when 9:10pm Blackboard jobs complete). Additional jobs will be scheduled via TIDAL and should complete well before 12:55am. (see list below) Data Warehouse job - must complete before taking the system down HIgher One - Ben will have prod control shut off the interface so nothing else processes | 5 | Open | 2018-04-27 22:00 | 2018-04-27 22:05 | Cornell (Maureen)
7 | Prod control to send email to DM on call team once Batch TIDAL (replication refresh) job completes NOTE: if job has not run by 11pm - send email to DM team | 5 | Open | 2018-04-27 23:00 | 2018-04-27 23:05 | Cornell (Maureen)
8 | DM Team to notify IBM when replication job completes | 5 | Open | 2018-04-27 23:05 |  | Cornell (Garry Chen)
9 | PM Email Status |  | Open | 2018-04-28 01:00 |  | IBM PM
10 | Bring down Services, bring down Web Server to invoke "Sorry" Page | 30 | Open | 2018-04-28 01:00 | 2018-04-28 01:30 | IBM Upgrade | Confirm (CUCCJOB have completed by 12:40 am EST - if they are not complete: give Amber a call to review jobs - this job run only
11 | Backup Database, Apps/Web PS_Home Backup and Installations(2 Web Servers, 6 App Servers, 1 PRCS, 1 NT) This step needed for Tools Upgrades only | 60 | Open | 2018-04-28 01:00 | 2018-04-28 02:00 | IBM Upgrade
12 | Verify backup is complete | 15 | Open | 2018-04-28 02:00 | 2018-04-28 02:15 | IBM Upgrade
13 | Backup tables: ps_cu_id_card and ps_cu_id_card_inac --should be after backup completes | 15 | Open | 2018-04-28 02:00 | 2018-04-28 02:15 | IBM Upgrade
| Tools Patch Upgrade Process | 0 | Open | 2018-04-28 02:00 | 2018-04-28 02:00 | IBM Upgrade
| Verification and Validation | 0 | Open | 2018-04-28 02:00 | 2018-04-28 02:00 | IBM Upgrade
14 | Project Copy Include: CHGxxx | 300 | Open | 2018-04-28 02:00 | 2018-04-28 07:00 | IBM Upgrade
15 | PM Email Status |  | Open | 2018-04-28 08:00 |  | IBM PM
| Refresh X92SCOR with Thursday's Copy of P92SCOR *** Complete Solix Data Masking after refresh") Not needed for this Project move | 960 | Open |  | 0.66667 | IBM Upgrade
| Project Build/DMS Executions | 0 | Open | 2018-04-28 07:00 | 2018-04-28 07:00 | IBM Upgrade
| PM Email Status |  | Open | 2018-04-28 12:00 |  | IBM PM
16 | Verification and UAT Jira Issues validation | 60 | Open | 2018-04-28 07:00 | 2018-04-28 08:00 | IBM Upgrade
17 | Contact SSC & email group | 0 | Open | 2018-04-28 08:00 |  | IBM PM
18 | Notify Lisa (OUR)/ Greg(PC) with "1 hour to go" message | 0 | Open | 2018-04-28 08:00 |  | Cornell
19 | SSC complete manual steps, test P92 * Add Developer access back in A92 (can be done after releasing P92 to Cornell) - Sherri King, Sameer Shaik, Chris Rigsby) | 60 | Open | 2018-04-28 08:00 | 2018-04-28 09:00 | IBM SSC
20 | SSC notify PM complete | 5 | Open | 2018-04-28 09:00 | 2018-04-28 09:05 | IBM SSC
21 | PM contact Cornell/email group | 5 | Open | 2018-04-28 09:05 | 2018-04-28 09:10 | IBM PM
22 | Cornell users login to P92 to verify: INCLUDING releasing jobs previously placed on HOLD Due to PeopleTools Upgrade: Ben will need to turn the interface back on for Higher One Greg will be Prod Control resource for cutover | 120 | Open | 2018-04-28 09:10 | 2018-04-28 11:10 | Cornell
23 | Notify IBM when Testing Complete and Send out notifications that system is back | 5 | Open | 2018-04-28 11:10 | 2018-04-28 11:15 | Cornell
24 | Send email to DM team - they can begin their total refresh activities NOTE: the next time Data Mart will load again is Monday evening Notify After Hours Suppormt (255-5500) to update IT Services page that process is complete. |  | Open | 2018-04-28 11:15 |  | Cornell -Sherri
25 | Roll Back with backup's taken in Step 11 | 300 | Open |  |  | IBM Upgrade
26 | Refresh B92SCOR with Saturday COP AFTER Upgrade complete *** Complete Solix Data Masking after refresh *** Will be available Monday morning *** Developers shoud have provided list of migrations for Monday morning | 780 | Open | 2018-04-28 11:15 |  | IBM Upgrade
27 | Refresh X92SCOR to sync with Image 7/8 including post refresh steps specific to X92 | TBD | Open |  |  | IBM Upgrade
| JOB Details | Schedule for 1 AM Down Time |  |  |  | Image 6 - Down at 1 AM & Up at 7:10 AM on 9/23
| TIDAL PSPROD Connection Status | Schedule the PSPROD/P92SCOR TIDAL Connection to go into a Maintenance window at 1:00 am |  |  |  | 1:00 am to 7:10 am
| Grad Admissions After EAPJOBCU (23-01-EA) | Runs after EAPJOBCU and potentially after 10 PM |  |  |  | Confirmed by Mariah: Hold Grad Admissions After EAPJOBCU (23-01-EA) group on 9/22 to be run last on 9/23
| Higher One interface (06-35-04) (Manual) | Run step 1 to stop the Higher One interface |  |  |  | Confirmed by Ben Stein: Run Step 1 of 06-35-04 manually at 9 pm
| SCC_SI_RELS (09-03-24) | Runs every hour starting 12:05 am |  |  |  | Confirmed by Lisa Clark: Cancel jobs between 1:05 am to 6:05 am; Run the 7:05 am job when the system is back up.
| Blackboard Series (09-04-15) | Runs 3x per day; 7:10 am, 2:10 pm, 9:10 pm |  |  |  | Confirmed by Lisa Clark: Cancel the 7:10 am
| CUETRANS (09-07-05) | Runs every 15 minutes |  |  |  | Confirmed by Lisa Clark: Cancel jobs from 9/22 at 5:00 pm to 9/23 at 7 am; Hold 7:15 am jobs and run 2nd after the system is back up
| AVP616CU (17-60-15) | Runs at 1:05 am and 5:30 pm |  |  |  | Confirmed with Tilly; Cancel the 1:05 am run
| AECU_EDSUPDT (30-05-15) | Runs at 1:05 am and 5:30 pm - need to let transportation and campus life know (Lisa will let them know) |  |  |  | Confirmed by Rob: Cancel the 1:05 AM run
| AECU_ID_CARD Both (09-08-10) | Runs at 1:05 am and 5:33 pm |  |  |  | Confirmed by Lisa Clark & Rob Bandler; Cancel 1:05 am
| FTPCU aecu_id_card (09-08-10F) | Runs at 1:27 and 5:52 pm |  |  |  | Confirmed by Lisa Clark & Rob Bandler; Cancel 1:27 am
| DYNROLE_PUBL (09-00-30) | Runs at 4:00 am |  |  |  | Confirmed by Lisa Clark; Hold 4:00 am and run 1st after the system is back up
| AECU_CEMD004 SABA (70-00-05) | runs at 3:00 am |  |  |  | Confirmed by Chris Brown; Hold 3:00 am and release after the system is back up
| CUMBR (17-40-05) | Runs at 4:45 am |  |  |  | Confirmed by Tilly; Hold and release after the system is back up
| Person Data Load (17-70-00) 11:00 PM Friday Move file from Bastion to PSFTP (No PS Processes) | Run this process anytime during the day Friday after the file is rec’d at Bastion (usually between 2 and 3 pm) |  |  |  | No change
| CUSQL034 Reset Print Count (09-08-05) 11:00 PM Friday | Override to run at 6:30pm Friday |  |  |  | No change
| CUCCJOB (01-05-60) 12:05 AM Saturday | Hold & release after system comes back |  |  |  | No change
| AECU_EMN_OUT (30-10-00) | Runs at 8:00 am |  |  |  | No change
| JOB Details | Image 6 - Down at 1 AM & Up at 7:10 AM on 9/23
| TIDAL PSPROD Connection Status | 1:00 am to 7:10 am
| Grad Admissions After EAPJOBCU (23-01-EA) | Hold job group on 9/22 and run last on 9/23
| Higher One interface (06-35-04) (Manual) | Run Step 1 of 06-35-04 manually at 9 pm on 9/22
| SCC_SI_RELS (09-03-24) | Cancel jobs between 1:05 am to 3:05 pm; Run the 7:05 pm job when the system is back up
| Blackboard Series (09-04-15) | Cancel the 7:10 am run
| CUETRANS (09-07-05) | Cancel jobs from 9/22 at 5:00 pm to 9/23 at 7 am Hold 7:15 am job and run 2nd after the system is back up
| AVP616CU (17-60-15) | Cancel the 1:05 am run
| AECU_EDSUPDT (30-05-15) | Cancel the 1:05 am run
| AEU_ID_CARD Both (09-08-10) | Cancel 1:05 am run
| FTPCU aecu_id_card (09-08-10F) | Cancel 1:27 am run
| DYNROLE_PUBL (09-00-30) | Hold 4 am run and run 1st after the system is back up
| AECU_CEMD004 SABA (70-00-05) | Hold 3 am run and release after the system is back up
| CUMBR (17-40-05) | Hold 4:45 am run and run after the system is back up
| Person Data Load (17-70-00) 11:00 PM Friday Move file from Bastion to PSFTP (No PS Processes) | Run normal schedule
| CUSQL034 Reset Print Count (09-08-05) 11:00 PM Friday | Run normal schedule
| CUCCJOB (01-05-60) 12:05 AM Saturday | Run normal schedule
| AECU_EMN_OUT (30-10-00) | Run normal schedule
Formulas:
End Time (EST) = +[Start Time (EST)]+([Duration (min)]/24/60)
Start Time (EST) = +[End Time (EST), row above]+(355/24/60)
Start Time (EST) = +[End Time (EST), row above]

## Issues
Issue No | Opened By | Status | Assigned | Date Open | Issue | Description | Updates

## Authorization
Name | Business Area | Jira # |  | Signoff during Prod Cutover or Later | Other Contacts
Lloyd Hall | Admissions |  |  | Monday
Tilly Garnett | Contributor Relations |  |  | Monday | Ron Babuka (Image 5)
Colleen Wright | Financial Aid |  |  | Monday | Shannon Sessler, Jennifer Talcott
Brenda D'Angelo | Grad |  |  | Monday | Brad
Sherri King | IT |  |  | Prod | Rob Bandler
Amber Aiken | Prod Control |  |  | Prod (Sherri call Greg 1 hr ahead of testing | Greg Marvin (Image 5),Christina Bucko | y
Bill Webster | SEVIS |  |  | Monday
Nicole Waterman | Student Employment |  |  | Monday |  | -
Ben Stein | Student Financials |  |  | Monday Saturday when Tools ins included - Higher One | Brian Kay
Lisa Clark | Student Records |  |  | Prod (Sherri call Lisa 1 hr ahead of testing) | Aryn Taylor, Matt Bell | y
Sid Cuff | Workday |  |  | Monday
| Campus Community |  |  |  | list each area and owner Student Svcs Center: 22691158
Vicky Mikula | Sponsor
Garry Chen | Dmart ON Call Team |  |  |  | Tom Sessler, Jeff Christen (607-255-9207), Derek Messie
^ comments included in excel comment for each approval
Note on C4: ncoultas: FA is signing off except for the following: Security analysis- pending ticket? FA history- reported JIRA Query Tree additions- reported JIRA