PeopleSoft CS Bundle 39 Schedule:

|  |  |  |
| --- | --- | --- |
| **Step** | **Start** | **End** |
| AT&T Refresh U90SCOR, complete masking* 10/20/15 Copy of Production
 | 10/21/15 | 10/22/15 |
| Oracle Release of Bundle 39 | 10/23/15 |  |
| AT&T Apply Bundle 39 to M90/U90 | 10/24/15 | 10/27/15 |
| AT&T Complete retrofits in U90, impact analysis | 10/28/15 | 11/04/15 |
| Refresh A90SCOR, complete masking* 10/30/15 Copy of Production
* Code Freeze in Effect (non-emergency)
* A90SCOR no longer available until 11/23
* Alternate Migration Path in Progress
 | 10/31/15 | 11/01/15 |
| AT&T Deliver Impact Analysis to Cornell | 11/05/15 | 11/05/15 |
| AT&T SSC manual steps and validation* Include Security Step
 | 11/05/15 | 11/05/15 |
| AT&T complete A90 Test move* Outage timings to be compiled after
 | 11/05/15 | 11/06/15 |
| AT&T SSC Manual steps | 11/09/15 | 11/09/15 |
| Cornell UAT | 11/09/15 | 11/18/15 |
| Production move | 11/20/15 | 11/21/15 |